## Sheet1
Project schedule
|  | PROJECT WEEK | To do | SEP |  |  |  | OCT |  |  |  |  | NOV |  |  |  | DEC
|  |  |  | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11
| Junhong Min |  | Voice Recognition using STT | SEP 4: Proposal; OCT 23: Midterm Exam; OCT 30: Midterm Demo; DEC 4: Final Demo; DEC 11: Final Report
Voice Recognition with Proximity Sensor | bar: OCT 9
Voice Recognition combined with video function | bar: NOV 6
UI_main_menu | bar: OCT 16
UI_custom_list with search | bar: OCT 16
Take good care of the fridge | bar: NOV 6
Recommendation Algorithm | bar: NOV 6 to NOV 13
Gamificaiton | bar: NOV 27
Ui_community | bar: NOV 20
Ui upgrade | bar: NOV 27
| Jaewon Lee |  | Playing Youtube in activity sequentially | bar: OCT 2
Construct DB server | bar: OCT 9
Get DB info and Set DB info via php | bar: OCT 16
Interlocking youtube video with Voice Recognition | bar: NOV 6
Interlocking DB with recipe page | bar: NOV 6
Interlocking DB with recipe upload page and search page | bar: NOV 6
Interlocking DB with Take good care and recommendation algo | bar: NOV 20 to NOV 27
Interlocking with conditional search | bar: NOV 20
login function | bar: NOV 13
Mypage function | bar: NOV 20 to NOV 27
| Hyeonwoo Park |  | UI_recipe_page | bar: OCT 2
UI_video_page_mockup | bar: OCT 9
UI _recipe_upload_page | bar: OCT 16; NOV 6
UI_video_page | bar: NOV 6
UI_conditional_search | bar: NOV 13
UI_evaluation_page | bar: NOV 13
Ui upgrade | bar: NOV 20 to NOV 27